## I3
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | Home | 1.02 | Admin Portal | Design the landing page for Admin | 2019-11-08 | 2019-11-13 | 100% | Abhijeet
2 | Home | 1.02 | Admin Portal | Add the backend logic for Admin | 2019-11-09 | 2019-11-13 | 100% | Abhijeet
3 | Home | 1.02 | Admin Portal | Test if admin is able to customize the price and website content | 2019-11-10 | 2019-11-13 | 100% | Abhijeet
4 | Delivery Management | 3.02 | Change Delivery Address | Modify the code from previous iteration to display the changes in the same session | 2019-11-11 | 2019-11-15 | 100% | Abhijeet
5 | Delivery Management | 3.02 | Change Delivery Address | Test if changes are reflected on the portal in the same session. | 2019-11-14 | 2019-11-18 | 100% | Murtaza
7 | Order Management | 5.07 | Order History | Design page to display the list of orders | 2019-11-15 | 2019-11-18 | 100% | Ansley
8 | Order Management | 5.07 | Order History | Add backend logic to get the historical data from firebase | 2019-11-16 | 2019-11-18 | 100% | Ansley
9 | Order Management | 5.07 | Order History | Handle the scenarios of pagenation etc | 2019-11-17 | 2019-11-18 | 100% | Ansley
10 | Order Management | 5.07 | Order History | Add button to clear the history | 2019-11-18 | 2019-11-18 | 100% | Ansley
11 | Notification Management | 7.01 | Order Receipt | Research about API or functions which can be used to trigger email/text message | 2019-11-20 | 2019-11-21 | 100% | Murtaza
12 | Notification Management | 7.01 | Order Receipt | Design the notification mail/text | 2019-11-21 | 2019-11-22 | 100% | Murtaza
13 | Notification Management | 7.01 | Order Receipt | Code the notification functionality | 2019-11-22 | 2019-11-23 | 100% | Murtaza
14 | Notification Management | 7.01 | Order Receipt | Check if the notifications are correctly pushed at each stage | 2019-11-23 | 2019-11-24 | 100% | Murtaza
15 | Customer Support | 8.02 | Feedbacks and Suggestions | Design a web page to accept free text of suggestions and some questions to get the feedback | 2019-11-27 | 2019-11-30 | 100% | Abhijeet
16 | Customer Support | 8.02 | Feedbacks and Suggestions | Make the changes in Database to store the suggestions and feedbacl | 2019-11-28 | 2019-11-30 | 100% | Abhijeet
17 | Customer Support | 8.02 | Feedbacks and Suggestions | Write backend logic to store and retrieve the suggestions/feedback | 2019-11-29 | 2019-11-30 | 100% | Abhijeet
18 | Customer Support | 8.02 | Feedbacks and Suggestions | Test if user is able to give suggestions/feedback and check if it is getting stored in database | 2019-11-30 | 11/31/2019 | 100% | Abhijeet

## I4
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | Home | 1.02 | Admin Portal | Design the landing page for Admin | 2019-12-06 | 2019-12-08 | 100% | Ansley
2 | Home | 1.02 | Admin Portal | Add the backend logic for Admin | 2019-12-07 | 2019-12-08 | 100% | Ansley
3 | Home | 1.02 | Admin Portal | Test if admin is able to customize the price and website content | 2019-12-08 | 2019-12-10 | 100% | Ansley
4 | Account Management | 5.05 | Delete Account | Add button to delete the account | 2019-12-09 | 2019-12-10 | 100% | Abhijeet
5 | Account Management | 5.05 | Delete Account | Develop backend code to set the delete flag in database | 2019-12-10 | 2019-12-10 | 100% | Abhijeet
6 | Account Management | 5.05 | Delete Account | Check if db gets updated correctly and user should not be able to login again | 2019-12-11 | 2019-12-12 | 100% | Abhijeet
7 | Account Management | 5.06 | Configure Account | Add edit button on user profile | 2019-12-12 | 2019-12-16 | 100% | Ansley
8 | Account Management | 5.06 | Configure Account | Make the fields editable | 2019-12-13 | 2019-12-16 | 100% | Ansley
9 | Account Management | 5.06 | Configure Account | Add logic to update the database | 2019-12-14 | 2019-12-18 | 100% | Ansley
10 | Account Management | 5.06 | Configure Account | Test the changes | 2019-12-15 | 2019-12-17 | 100% | Ansley
11 | Payement Management | 6.05 | Delete Payment Method | Add delete button to remove payement method | 2019-12-16 | 2019-12-17 | 100% | Ansley
12 | Payement Management | 6.05 | Delete Payment Method | Add logic to remove the payement method data from DB | 2019-12-16 | 2019-12-17 | 100% | Ansley
13 | Payement Management | 6.05 | Delete Payment Method | Test the changes | 2019-12-18 | 2019-12-20 | 100% | Ansley
14 | Customer Support. | 8.01 | Contact Customer Support. | Analyze the current implementation to see how to integrate the customer support module. | 2019-12-17 | 2019-12-17 | 100% | Ansley
15 | Customer Support. | 8.01 | Contact Customer Support. | Design the frontend as well as backend for the customer support. | 2019-12-17 | 2019-12-18 | 100% | Ansley
16 | Customer Support. | 8.01 | Contact Customer Support. | Test if user can post the comments for the customer support on the portal. | 2019-12-20 | 2019-12-18 | 100% | Ansley
17 | Notification Management. | 7.02 | Notify user through email. | Find an API to send an email to user | 2019-12-12 | 2019-12-11 | 100% | Ansley
18 | Notification Management. | 7.02 | Notify user through email. | Develop backend code to trigger the email using API | 2019-12-12 | 2019-12-11 | 100% | Ansley
19 | Notification Management. | 7.02 | Notify user through email. | Test if user is receiving emails about the order update. | 2019-12-16 | 2019-12-11 | 100% | Ashish