## Road Map I1
My Personal Chef
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 10/05/19 | Iteration 2 - 10/25/19 | Iteration 3 - 11/08/19 | Iteration 4 - 12/06/19
Module 1 - Home | 01.01 User Portal | 4 |  | x
| 01.02 Admin Portal | 3 |  |  | x | x
Module 2 -Order Management | 02.01 Search content | 3 | x
| 02.02 Customize and Order. | 3 |  |  |  | x
| 02.03 Cancel the order. | 2 | x
Module 3 - Delivery Management | 03.01 Track the delivery | 3 |  |  | x
| 03.02 Change Delivery Address. | 2 | x |  | x
| 03.03 Add delivery Instructions. | 1 | x
Module 4 - Subscription Management | 04.01 Prepare monthly/weekly plan. | 2 |  | x
| 04.02 Alter/Cancel Subscription. | 2 |  |  |  | x
| 04.03 Manage Subscription. | 3 |  |  | x
| 04.04 Subscription Type Management. | 3 |  |  | x
Module 5 - User Account Management | 05.01 Open My Account | 2 | x
| 05.02 Login into account | 2 | x |  | x
| 05.03 Sign Up using Existing Accounts. | 1 |  | x
| 05.04 Modify User Information. | 2 |  | x
| 05.05 Delete Account. | 1 |  |  |  | x
| 05.06 Configure Account. | 3 |  |  |  | x
| 05.07 Order History. | 2 |  |  | x
Module 6 - Payment Management | 06.01 Make Payment | 3 |  | x
| 06.02 Add Payment Details. | 2 |  | x
| 06.03 Add multiple cards. | 2 |  |  |  | x
| 06.04 Pay using wallets. | 2 |  |  |  | x
| 06.05 Delete Payment Details. | 2 |  |  |  | x
Module 7 - Notification Management. | 07.01 Order Receipts. | 3 |  |  | x
| 07.02 Notify user through email. | 2 |  |  |  | x
Module 8 - Customer Support. | 08.01 Contact Customer Support. | 1 |  |  |  | x
| 08.02 Feedbacks and Suggestions. | 1 |  |  | x
Module 9 - Supply Management | 09.01 Add Ingredients/Price. | 2 | x
| 09.02 Edit Ingredients/Pirce. | 2 | x
| 09.03 Delete Ingredients/Price. | 2 | x
|  | Velocity : | 18 | 14 | 25 | 21

## Road Map I2
My Personal Chef
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 10/05/19 | Iteration 2 - 10/25/19 | Iteration 3 - 11/08/19 | Iteration 4 - 12/06/19
Module 1 - Home | 01.01 User Portal | 4 |  | x
| 01.02 Admin Portal | 3 |  |  | x | x
Module 2 -Order Management | 02.01 Search content | 3 | x
| 02.02 Customize and Order. | 3 |  |  |  | x
| 02.03 Cancel the order. | 2 | x
Module 3 - Delivery Management | 03.01 Track the delivery | 3 |  |  | x
| 03.02 Change Delivery Address. | 2 | x |  | x
| 03.03 Add delivery Instructions. | 1 | x
Module 4 - Subscription Management | 04.01 Prepare monthly/weekly plan. | 2 |  | x
| 04.02 Alter/Cancel Subscription. | 2 |  |  |  | x
| 04.03 Manage Subscription. | 3 |  |  | x
| 04.04 Subscription Type Management. | 3 |  |  | x
Module 5 - User Account Management | 05.01 Open My Account | 2 | x
| 05.02 Login into account | 2 | x |  | x
| 05.03 Sign Up using Existing Accounts. | 1 |  | x
| 05.04 Modify User Information. | 2 |  | x
| 05.05 Delete Account. | 1 |  |  |  | x
| 05.06 Configure Account. | 3 |  |  |  | x
| 05.07 Order History. | 2 |  |  | x
Module 6 - Payment Management | 06.01 Make Payment | 3 |  | x
| 06.02 Add Payment Details. | 2 |  | x
| 06.03 Add multiple cards. | 2 |  |  |  | x
| 06.04 Pay using wallets. | 2 |  |  |  | x
| 06.05 Delete Payment Details. | 2 |  |  |  | x
Module 7 - Notification Management. | 07.01 Order Receipts. | 3 |  |  | x
| 07.02 Notify user through email. | 2 |  |  |  | x
Module 8 - Customer Support. | 08.01 Contact Customer Support. | 1 |  |  |  | x
| 08.02 Feedbacks and Suggestions. | 1 |  |  | x
Module 9 - Supply Management | 09.01 Add Ingredients/Price. | 2 | x
| 09.02 Edit Ingredients/Pirce. | 2 | x
| 09.03 Delete Ingredients/Price. | 2 | x
|  | Velocity : | 18 | 14 | 25 | 21

## Roles Traceability
User Roles vs. Features Matrix
Actors
Application Modules | Feature Backlog | User | Guest | Admin
Module 1 - Home | 01.01 User Portal | x
| 01.02 Admin Portal | x |  | x
Module 2 -Order Management | 02.01 Search content | x | x | x
| 02.02 Customize and Order. | x
| 02.03 Cancel the order. | x | x | x
Module 3 - Delivery Management | 03.01 Track the delivery | x
| 03.02 Change Delivery Address. | x | x
| 03.03 Add delivery Instructions. | x | x
Module 4 - Subscription Management | 04.01 Prepare monthly/weekly plan. | x |  | x
| 04.02 Alter/Cancel Subscription. | x
| 04.03 Manage Subscription. | x
| 04.04 Subscription Type Management. | x |  | x
Module 5 - User Account Management | 05.01 Open My Account | x | x
| 05.02 Login into account | x |  | x
| 05.03 Sign Up using Existing Accounts. | x | x
| 05.04 Modify User Information. | x |  | x
| 05.05 Delete Account. | x |  | x
| 05.06 Configure Account. | x
| 05.07 Order History. | x
Module 6 - Payment Management | 06.01 Make Payment | x | x
| 06.02 Add Payment Details. | x
| 06.03 Add multiple cards. | x
| 06.04 Pay using wallets. | x | x
| 06.05 Delete Payment Details. | x |  | x
Module 7 - Notification Management. | 07.01 Order Receipts. | x
| 07.02 Notify user through email. | x | x
Module 8 - Customer Support. | 08.01 Contact Customer Support. | x | x
| 08.02 Feedbacks and Suggestions. | x
Module 9 - Supply Management | 09.01 Add Ingredients/Price.
| 09.02 Edit Ingredients/Pirce. |  |  | x
| 09.03 Delete Ingredients/Price. |  |  | x

## Role Descriptions
User Roles
1. Guest (unregistered user) can chek the recipes and order them as a guest user. Someone who is not logged in.
2. User (registered user) can view , order, make payments, modify order etc.
3. Admin can add/ edit/ delete prices of ingredients and access the admin