## I1
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | User Account Management | 5.01 | Open User Account | Design the registartion form | 2019-09-30 | 2019-09-30 | Complete | Abhijit
2 | User Account Management | 5.01 | Open User Account | Implement the code using Firbase | 2019-09-30 | 2019-10-01 | Complete | Abhijit
3 | User Account Management | 5.01 | Open User Account | Test the firebase setup and account creation functionality | 2019-10-01 | 2019-10-01 | Complete | Abhijit
4 | User Account Management | 5.02 | Login Into Account | Design the login page | 2019-10-01 | 2019-10-01 | Complete | Abhijit
5 | User Account Management | 5.02 | Login Into Account | Implement the login code | 2019-10-01 | 2019-10-01 | Complete | Murtaza
6 | User Account Management | 5.02 | Login Into Account | Test the login-logout functionality | 2019-10-01 | 2019-10-02 | Complete | Murtaza
7 | Order Management | 2.01 | Search Content | Find the API for Menu | 2019-10-02 | 2019-10-02 | Complete | Ansley
8 | Order Management | 2.01 | Search Content | Implement the API | 2019-10-03 | 2019-10-03 | Complete | Ansley
9 | Order Management | 2.03 | Cancel Order | Implement the cancel functionality | 2019-10-09
10 | Order Management | 2.03 | Cancel Order | test the functionalty | 2019-10-10
11 | Delivery Management | 3.02 | Change delivery address | Add modify option for delivery detail | 2019-10-11
12 | Delivery Management | 3.02 | Change delivery address | test the functionalty | 2019-10-12
13 | Delivery Management | 3.03 | Add delivery instruction | Add additional free text box for adding instructions | 2019-10-13
14 | Delivery Management | 3.03 | Add delivery instruction | test the functionalty | 2019-10-14
15 | Supply Management | 9.01 | Add Ingredients | Add form to let admin create new ingrdients on website | 2019-10-15
16 | Supply Management | 9.01 | Add Ingredients | Implement the backend logic | 2019-10-16 | 2019-10-16 | complete | Ansley
17 | Supply Management | 9.01 | Add Ingredients | test the functionalty | 2019-10-17 | 2019-10-17 | complete | Ansley
18 | Supply Management | 9.02 | Edit Ingredients | Modify the exisitng form to add ingredients to incorporate this functionality | 2019-10-18 | 2019-10-19 | complete | Ansley
19 | Supply Management | 9.02 | Edit Ingredients | Modify the backend logic to handle update scenario | 2019-10-19 | 2019-10-19 | complete | Ansley
20 | Supply Management | 9.02 | Edit Ingredients | test the functionalty | 2019-10-20
21 | Supply Management | 9.03 | Delete Ingredients | Add delete button on the form | 2019-10-22 | 2019-10-22 | complete
22 | Supply Management | 9.03 | Delete Ingredients | add the backend logic for deletion | 2019-10-22 | 2019-10-25 | complete
23 | Supply Management | 9.03 | Delete Ingredients | test the logic | 2019-10-25 | 2019-10-25 | complete

## I2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | User Account Management | 5.03 | Sign Up using Existing Accounts. | Design registration option in webpage to sign up using existing social media account | 2019-10-21 | 2019-10-21 | completed | Ansley
2 | User Account Management | 5.03 | Sign Up using Existing Accounts. | Implement registration with existing accounts social media account | 2019-10-21 | 2019-10-23 | completed | Ansley
3 | User Account Management | 5.03 | Sign Up using Existing Accounts. | Test the functionality whether the user is able to login with existing social media account | 2019-10-24 | 2019-10-24 | completed | Ansley
4 | User Account Management | 5.04 | Modify User Information. | Design edit user information page | 2019-10-22 | 2019-10-22 | completed | Ansley
5 | User Account Management | 5.04 | Modify User Information. | Implement updating user information in system database of the user | 2019-10-23 | 2019-10-25 | completed | Ansley
6 | User Account Management | 5.04 | Modify User Information. | Test the edited information is updated in the database and reflected in user account | 2019-10-26 | 2019-10-26 | completed | Ansley
7 | Home | 1.01 | User Portal | Design user main page to view overview of the user account | 2019-10-22
8 | Home | 1.01 | User Portal | fetch all the user information details from database to user account | 2019-10-23
9 | Home | 1.01 | User Portal | Test the functionality of retriving all user details to the account | 2019-10-24
10 | Subscription Management | 4.01 | Prepare monthly/weekly plan. | Design an option for user to register for subscribtion montly or weekly plan | 2019-10-25 | 2019-10-30 | completed | Abhijit
11 | Subscription Management | 4.01 | Prepare monthly/weekly plan. | add or delete user from subscription list as per users opted subscription | 2019-10-26 | 2019-10-31 | completed | Abhijit
12 | Subscription Management | 4.01 | Prepare monthly/weekly plan. | check if the user is being aded to subscription list and removed once subscription ends | 2019-10-27 | 2019-10-31 | completed | Abhijit
13 | Payment Management | 6.01 | Make Payment | add a page for transaction / make payment option | 2019-10-28
14 | Payment Management | 6.01 | Make Payment | implement payment gateway once cliked pay for order | 2019-10-28
15 | Payment Management | 6.01 | Make Payment | test payment processing functionality | 2019-10-29
16 | Payment Management | 6.02 | Add Payment Details. | create options for user to add multiple payment details like creditcad or debitcard | 2019-10-30
17 | Payment Management | 6.02 | Add Payment Details. | check for valid payment details and store it securely in the database | 2019-10-30
18 | Payment Management | 6.02 | Add Payment Details. | test chang payment options for users having multiple payment details | 2019-10-31