## I1
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | User Account Management | 5.01 | Open User Account | Design the registartion form | 2019-09-30 | 2019-09-30 | Complete | Abhijeet
2 | User Account Management | 5.01 | Open User Account | Implement the code using Firbase | 2019-09-30 | 2019-10-01 | Complete | Abhijeet
3 | User Account Management | 5.01 | Open User Account | Test the firebase setup and account creation functionality | 2019-10-01 | 2019-10-01 | Complete | Abhijeet
4 | User Account Management | 5.02 | Login Into Account | Design the login page | 2019-10-01 | 2019-10-01 | Complete | Abhijeet
5 | User Account Management | 5.02 | Login Into Account | Implement the login code | 2019-10-01 | 2019-10-01 | Complete | Murtaza
6 | User Account Management | 5.02 | Login Into Account | Test the login-logout functionality | 2019-10-01 | 2019-10-02 | Complete | Murtaza
7 | Order Management | 2.01 | Search Content | Find the API for Menu | 2019-10-02 | 2019-10-02 | Complete | Ansley
8 | Order Management | 2.01 | Search Content | Implement the API | 2019-10-03 | 2019-10-03 | Complete | Ansley
9 | Order Management | 2.03 | Cancel Order | Implement the cancel functionality | 2019-10-09
10 | Order Management | 2.03 | Cancel Order | test the functionalty | 2019-10-10
11 | Delivery Management | 3.02 | Change delivery address | Add modify option for delivery detail | 2019-10-11
12 | Delivery Management | 3.02 | Change delivery address | test the functionalty | 2019-10-12
13 | Delivery Management | 3.03 | Add delivery instruction | Add additional free text box for adding instructions | 2019-10-13
14 | Delivery Management | 3.03 | Add delivery instruction | test the functionalty | 2019-10-14
15 | Supply Management | 9.01 | Add Ingredients | Add form to let admin create new ingrdients on website | 2019-10-15
16 | Supply Management | 9.01 | Add Ingredients | Implement the backend logic | 2019-10-16
17 | Supply Management | 9.01 | Add Ingredients | test the functionalty | 2019-10-17
18 | Supply Management | 9.02 | Edit Ingredients | Modify the exisitng form to add ingredients to incorporate this functionality | 2019-10-18
19 | Supply Management | 9.02 | Edit Ingredients | Modify the backend logic to handle update scenario | 2019-10-19
20 | Supply Management | 9.02 | Edit Ingredients | test the functionalty | 2019-10-20
21 | Supply Management | 9.03 | Delete Ingredients | Add delete button on the form | 2019-10-22
22 | Supply Management | 9.03 | Delete Ingredients | add the backend logic for deletion | 2019-10-22
23 | Supply Management | 9.03 | Delete Ingredients | test the logic | 2019-10-25

## I2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner